## Sheet1
S.No. | Title / Description | Cost (£)
1 | Project Development: - Website Development (6 Custom Pages) - Email Marketing Integration Setup (Mailchimp - Newsletter Subscription) - Lead Collection through Forms - Appointment Scheduling - Google Analytics Setup - GDPR, Privacy and other legal pages (3 Legal Pages) - Cookie Consent | 4500
2 | Web Hosting and Licenses: - CMS Setup (Wordpress) - Domain Name Setup and Integration - Website Hosting (Hosted on preferred cloud region) - Wordpress Plugin Licenses | 750
| Total | 5250
S.No. | Title / Description | Cost (£)
1 | Maintenance and Support*: - Server Maintenance - Downtime Support - Content Changes * Support does not cover new functionality or new pages, we can assist with bug fixes and minor enhancements to existing functionality. | 750 per month

## Sheet2
Task | Sub-Tasks | Start Date | End Date
Training | Training Call - 45 Minutes | 2023-07-20 | 2023-07-20
Functional Testing | Functional | 2023-07-19 | 2023-07-21
| Testing Fixes (if any) | 2023-07-20 | 2023-07-24
Migration & Integration | Includes all Data, Events and media migrations, integrations with third-party tools | 2023-07-20 | 2023-07-24
Design Testing | Design - Web | 2023-07-25 | 2023-07-27
| Design - Mobile | 2023-07-25 | 2023-07-27
| Testing Fixes - Final (if any) | 2023-07-25 | 2023-07-28
Go Live | Domain Transfer | 2023-07-29 | 2023-07-29
| Smoke Testing of the Website | 2023-07-29 | 2023-07-30
| Website Monitoring | 2023-07-30 | 2023-07-31
| Announcement to members | 2023-08-01

## Sheet3
First Name | Last Name
William | Smith
Davies | Okeowo
Zere | Iskinder
Emiliano | Fuerte
Emigdio | Valle
Juliet | Grant
Harvey | Shepard
Ulric | Parker
Azzurra | Marotta
Jacopo | Greece
Daniel | Evans
Ozawa | Nobuo
Akiyama | Iwao
Mohammed | Abara
Gillian | Madonsela
Katherine | Johnson
Marina | Cruz
Leelawati | Kar
Nitika | Sethi
Prabhat | Baral
Vivek | Jadoo
Vinod | Babu
Ajeesh | Mohan
Rekha | Balasubramanian
Jonah | Saarinen